## NDT
project name |  | MATERIAL INSPECTION REPORT |  |  |  | REPORT NO:
S.NO | TYPE OF MATERIAL | GRADE | Thikness | SIZE | HEAT NO | NOS | Remarks

## PUNCH CLEARANCE (hidden)
REQUEST FOR INSPECTION
INSPECTION SCHEDULE -PUNCH CLEARANCE
Sl. No. | Discipline: | Module | Type of Inspection | Test Pack No. | Inspection Date | Inspection Time | Contractor | Location | Inspection Level | REMARKS | STATUS | FWBS
1 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | GI-006 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-74-06
2 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WC-024 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-76-04
3 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | AI-019 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-07-06
4 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | AP-013 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-07-07
5 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WC-025 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-76-04
6 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | GI-007 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-74-03
7 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WD-010 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-51-11
8 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WD-011 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-51-11
9 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WH-027 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-72-05
10 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WH-028 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-72-05
11 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WP-019 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-51-11
12 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WC-036 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-76-08
13 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WC-037 | 2020-12-16 | 09:30 AM | ZIRCONO | HULL (OB) | W | PARTIALLY |  | FP-TS-76-08
14 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | GI-006 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-74-06
15 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WC-024 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-76-04
16 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | AI-019 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-07-06
17 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | AP-013 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-07-07
18 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WC-025 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-76-04
19 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | GI-007 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-74-03
20 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WD-010 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-51-11
21 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WD-011 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-51-11
22 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WH-027 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-72-05
23 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WH-028 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-72-05
24 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WP-019 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-51-11
25 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WC-036 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-76-08
26 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WC-037 | 2020-12-17 | 09.30AM | ZIRCONO | HULL (OB) | W | PARTIALLY | CONTINUE | FP-TS-76-08
27 | PIPING | VS00 | PUNCH CLEARANCE | AI-004 | 2021-01-20 | 09.30AM | PROSPER | HULL (OB) | W
28 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WC-036 | 2021-02-10 | 09.30AM | ZIRCONO | HULL (OB) | W
29 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | WC-037 | 2021-02-10 | 09.30AM | ZIRCONO | HULL (OB) | W
30 | PIPING | IG20 TO IG27 | PUNCH CLEARANCE | AP-013 | 2021-02-10 | 09.30AM | ZIRCONO | HULL (OB) | W
31 | PIPING | TS23 | PUNCH CLEARANCE | GF-042 | 2021-02-22 | 09.30AM | ZIRCONO | HULL (OB) | W
32 | PIPING | TS11 | PUNCH CLEARANCE | GF-041 | 2021-02-23 | 10.00AM | SMOP-PS | HULL (OB) | W |  |  | FP-TS-70-01
33 | PIPING | TS06 | PUNCH CLEARANCE | VA-039 | 2021-02-23 | 10.00AM | SMOP-PS | HULL (OB) | W |  |  | FP-TS-76-05

## RT FILM REVIEW (hidden)
REQUEST FOR INSPECTION
INSPECTION SCHEDULE - RT FILM REVIEW
Sl. No. | Discipline: | Type of Inspection | Inspection Date | Inspection Time | Location | Inspection Level | REMARKS
1 | PIPING | RT FILM REVIEW | 2021-11-03 | 02.00PM | PROJECT OFFICE -12, LEVEL-2 | R